## Slide 1: Finance & Operations: Q1 review and Q2 outlook
Q1 FY2026/27 (July to September 2026) | Outlook: October to December 2026
LoHo Learning Limited
Notes: Open with the purpose: review Q1 results across sales, finance and people operations, then agree Q2 priorities and the decisions needed. Allow about 25 minutes plus questions.

## Slide 2: FY26/27 strategy: five objectives we own
1 FY26/27 STRATEGY REVIEW
Objective | Measures we are held to | Actions
1.4 Financial resilience and investor readiness | Cash runway visibility of at least 6 months; 50% of B2B invoices paid within 30 days | 4
4.1 Safe and responsible work culture | Escalations resolved in SLA; tasks completed on time; 100% team participation per cycle | 4
4.2 Revenue-linked, equitable incentive programme | eNPS of at least 50 | 4
4.3 Capability: onboarding, succession, talent | Internal SLA compliance at least 90%; OKR achievement at least 70%; quarterly review completion at least 95% | 4
4.4 Rigorous performance management | 80% staff retention; internal promotion at least 30% of open roles | 5
Also owned: F2, fundraising documents consolidated in an investor data room.
Source: Q1 FY26/27 KPI Status, Finance and Operations.
Notes: These are the strategic objectives and measures from the Q1 KPI Status for Finance and Operations. We own 21 breakthrough actions across five objectives, plus F2 (fundraising data room). The strategy document itself did not arrive as a separate file; objectives and measures here come from the KPI status report. Check wording against the strategy.

## Slide 3: Q1 KPIs: 14 of 19 due actions delivered or on plan
2 Q1 PERFORMANCE REVIEW
Chart: Breakthrough actions by objective and Q1 status
| 1.4 Financial resilience | 4.1 Safe culture | 4.2 Incentives | 4.3 Capability | 4.4 Performance mgmt
Complete | 0 | 1 | 1 | 0 | 0
On plan | 4 | 1 | 1 | 2 | 4
Off plan, no recovery | 0 | 2 | 0 | 2 | 1
Not due in Q1 | 0 | 0 | 2 | 0 | 0
14 of 19
Delivered or on plan
2 complete, 12 on plan (74%)
5
Off plan, no recovery plan
Culture, capability and escalation paths
2
Not due in Q1
Bonus budget (Q2), mid-year review (Q3)
Source: Q1 FY26/27 KPI Status, Finance and Operations. 21 breakthrough actions in total.
Notes: Of 21 breakthrough actions, 19 were due in Q1. Two are complete, 12 are on plan, 5 are off plan without a recovery plan, and 2 are not due until Q2 and Q3. 14 of 19 is 74%. Five off-plan actions sit in culture, capability and performance management; financial resilience is fully on plan.

## Slide 4: Financial resilience: all four actions on plan
2 Q1 PERFORMANCE REVIEW
Action | Target | Q1 achieved | Status
1.4.1 Cash runway monitoring | Runway visibility of 6 months or more | Cash position report to the CEO every mid-month | On plan
1.4.2 Rolling 12-month forecast | Monthly board visibility | Sales tracker records revenue daily against targets; weekly Monday report | On plan
1.4.3 Collections discipline | 95% collections discipline; 50% of invoices paid in 30 days | Over 80% of receivables under 90 days overdue (September 2026) | On plan
F2 Fundraising data room | Documents ready in Q1 | Documents consolidated and kept updated | On plan
Next: reconcile debtor balances, agree accounts for escalation and set a dated recovery milestone, reviewed bi-weekly.
Source: Q1 FY26/27 KPI Status, Finance and Operations.
Notes: Objective 1.4. Measures: cash runway visibility of at least 6 months and 50% of B2B invoices paid within 30 days. The 95% collections discipline target is not yet reached: over 80% of receivables are under 90 days overdue. Next step is to reconcile debtor balances and agree accounts for escalation. The financial results that follow explain the numbers behind these actions.

## Slide 5: People and performance: 5 actions need recovery
2 Q1 PERFORMANCE REVIEW
Complete or on plan (14)
Staff survey and bonus system complete (4.1.1, 4.2.1)
Bonus rules set; staff briefing pending (4.2.2)
90-day onboarding and succession plan in place (4.3.1, 4.3.2)
Department OKRs and SLAs published (4.4.1, 4.4.2)
Quarterly review cycle on plan (4.4.3)
Learning from failure built into reviews (4.1.4)
Off plan, no recovery plan yet (5)
Safe Space meetings (4.1.2): schedule the first session
Manager feedback training (4.1.3): agree a date and owner
Rotation pilot (4.3.3): define participants, hosts and start date
Skills-gap assessment (4.3.4): complete for FY26/27
Escalation paths (4.4.4): document for critical functions
Measure for objective 4.2 is eNPS of 50 or more. The Q1 survey result is below that target.
Source: Q1 FY26/27 KPI Status; Q1 HR Report.
Notes: Objectives 4.1 to 4.4. Left: what is complete or on plan. Right: the five off-plan actions and the recovery step in the KPI report. 4.1.3 has no recovery step recorded; agree one. The eNPS measure for objective 4.2 is at least 50. HR reports the Q1 survey eNPS as -75 in its table and 40 in its summary; either figure is below target. Confirm with HR before presenting a number.

## Slide 6: Q1: sales reached 63% of target
KES 3.79M
Q1 sales
Target KES 5.97M (63.4%)
KES 2.19M
Shortfall to target
Elimu Pepe and Devices: KES 4.12M short
17
Headcount
12 permanent, 5 consultants; +2, no exits
-KES 3.06M
Q1 operating result
What the numbers say
CaaS eBooks (147% of target) and MTN Academy (KES 1.5M, unbudgeted) carried the quarter.
Elimu Pepe (21%) and LoHo Devices (9%) are the recovery priority for Q2.
2 Q1 PERFORMANCE REVIEW
Notes: Lead with the headline: 63.4% of target, KES 2.19M short. Be clear that the operating result is a management view from the chart of accounts, unaudited and before tax. The point to land: revenue is concentrated in two lines, and the two lines that missed are the ones with the largest targets.

## Slide 7: Sales by line
Chart: KES millions
| CaaS eBooks | Elimu Pepe | LoHo Devices | MTN Academy (Ug)
Q1 target | 0.923 | 3.85 | 1.2005 | 0
Q1 achieved | 1.359 | 0.82 | 0.107 | 1.5
Variance to target
eBooks: +KES 436K (147.3%)
Elimu Pepe: -KES 3.03M (21.3%)
Devices: -KES 1.09M (8.9%)
MTN Academy: +KES 1.5M, no target set
LoHo Campus: no target, no sales
Source: Q1 Target vs Achieved Report, quarter ended 30 September 2026. Amounts in KES.
2 Q1 PERFORMANCE REVIEW
Notes: Elimu Pepe carried 64% of the total target (KES 3.85M of 5.97M), so its miss explains most of the gap. MTN Academy had no target; without it the quarter would have been KES 2.29M, or 38% of target. Do not name individual staff on screen; keep staff-level results for the sales head.

## Slide 8: Q1 P&L
Q1 FY2026/27 | KES | % of sales
Sales | 3,786,384 | 100.0%
Cost of sales | (1,647,622) | 43.5%
Gross profit | 2,138,762 | 56.5%
Staff costs | (2,105,859) | 55.6%
Amortisation and depreciation | (1,894,031) | 50.0%
Other cost- Admin, sales & Marketing | (1,203,087) | 31.8%
Net operating result | (3,064,215) | -80.9%
KES 1.04M
Loss before non-cash items
Excludes amortisation and depreciation of KES 2.03M
Staff costs are 56% of sales. At a 57% gross margin, sales must roughly double before payroll is covered.
Source: Chart of Accounts, Q1 net change (management view, unaudited, before tax and closing adjustments). Cost of sales includes KES 250K cash discounts.
2 Q1 PERFORMANCE REVIEW
Notes: Figures are Q1 net changes from the chart of accounts. Amortisation: KES 1.88M in administration plus KES 0.13M in cost of sales (software). The cash-basis loss is an approximation to show the operating gap excluding non-cash charges. Check: 3,786,384 - 1,647,622 = 2,138,762; opex 5,202,977.

## Slide 9: Where the KES 5.2M of operating costs went
Chart: KES millions
| Staff costs | Amortisation (software) | Other admin | Sales & marketing | Telephone & internet | Depreciation & repairs
Q1 operating costs | 2.106 | 1.882 | 0.903 | 0.262 | 0.035 | 0.015
Worth a conversation
Staff costs: 40% of operating costs
Amortisation: 36%, non-cash
Consultancy KES 345K and software support KES 197K
Local travel KES 167K
Bank charges KES 83K
Source: Chart of Accounts, Q1 net change. Other admin includes consultancy, travel, legal, software support and bank charges.
2 Q1 PERFORMANCE REVIEW
Notes: Percentages are shares of KES 5,202,977 operating costs. Bank charges of KES 83K in a quarter are high relative to cash held; worth a check on tariffs and the number of accounts.

## Slide 10: Liquidity: obligations far exceed cash
KES 0.77M
Cash and bank
Standard Chartered, Sidian, petty cash
KES 4.03M
Net trade receivables
After KES 1.3M provision; gross KES 5.33M
KES 11.77M
Trade payables
Supplier balances at 30 September
KES 19.30M
Payroll-related payables
Includes statutory control accounts
What matters for Q2
Collections worked: gross trade receivables fell by KES 4.10M in Q1, more than the KES 3.79M billed.
Current assets of KES 4.99M against current liabilities of KES 31.21M. Cash alone covers about 2% of liabilities.
Statutory balances (PAYE, NSSF, NHIF, Housing Levy, HELB) total about KES 4.2M.
Source: Chart of Accounts, balance at 30 September 2026 (unaudited). Receivables movement is the Q1 net change on local trade receivables.
2 Q1 PERFORMANCE REVIEW
Notes: Be ready to explain what the payroll payables of KES 19.3M are made of: net salary control 3.33M, payroll payables 11.68M and statutory control accounts about 4.2M. Several statutory accounts show no Q1 movement, so check with payroll whether remittances were posted. Do not present these as arrears until confirmed.

## Slide 11: Q1 learnings: what to keep and what to change
2 Q1 PERFORMANCE REVIEW
What worked
Cash runway report to the CEO every mid-month
Over 80% of receivables under 90 days overdue; balances down KES 4.10M
Staff survey and bonus system completed
eBooks at 147% of target
What did not work
5 of 19 due actions off plan with no recovery plan
Elimu Pepe (21%) and Devices (9%) far below target
Survey eNPS below the target of 50
75% of sales from two lines
Carry forward or change
Carry: mid-month runway report and bi-weekly collections review
Change: an owner, date and recovery step for every off-plan action
Change: monthly targets and owners for each revenue line
Change: review statutory balances every month
Notes: What worked, what did not, what we carry forward or change. About one minute per column.

## Slide 12: Q2 target: KES 28.5M, 7.5 times Q1 sales
3 Q2 PRIORITIES & EXECUTION
Chart: KES millions
| CaaS eBooks | Elimu Pepe | LoHo Devices | LoHo Campus | MTN Academy (Ug)
Q1 achieved | 1.359 | 0.82 | 0.107 | 0 | 1.5
Q2 target | 3.147 | 13.626 | 4.9065 | 3.9065 | 2.942
KES 28.5M
Q2 sales target
October to December 2026
48%
Elimu Pepe share of Q2
KES 13.6M, up from KES 0.8M in Q1
KES 126M
Full-year target
Q1 delivered 3%; KES 122M left for 9 months
Source: Target - revenue workbook. Monthly Q2 targets: October KES 8.19M, November KES 9.12M, December KES 11.22M.
Notes: Q2 target of 28,527,848 is 7.5 times Q1 actual sales (3,786,348) and 4.8 times the Q1 target (5,973,500). Monthly: Oct 8,185,000; Nov 9,121,000; Dec 11,221,848. Campus had no Q1 sales and now carries KES 3.9M. Finance angle: set a cash and cost plan against this ramp, and ask Sales for the pipeline behind Elimu Pepe.

## Slide 13: Q2 revenue focus
Line | Q1 target (KES) | Q1 achieved (KES) | Variance (KES) | Q2 focus | Q2 target
CaaS eBooks | 923,000 | 1,359,161 | +436,161 | Sustain; protect margin | 3,147,000
Elimu Pepe | 3,850,000 | 819,797 | (3,030,203) | Recovery plan and pipeline review | 13,626,000
LoHo Devices | 1,200,500 | 107,390 | (1,093,110) | Review model, stock and channels | 4,906,500
MTN Academy (Ug) | none | 1,500,000 | +1,500,000 | Confirm contract and billing schedule | 2,941,848
LoHo Campus | none | 0 | n/a | Launch plan; no sales yet, first target | 3,906,500
Total | 5,973,500 | 3,786,348 | (2,187,152) |  | 28,527,848
Q2 target is 7.5 times Q1 sales. Finance needs a monthly cash and cost plan against it.
Source: Q1 Target vs Achieved Report; Target - revenue workbook (Q2 = October to December 2026). Q2 focus items are proposals for discussion.
3 Q2 PRIORITIES & EXECUTION
Notes: Q2 targets come from the revenue target workbook: eBooks 3.147M, Elimu Pepe 13.626M, Devices 4.9065M, Campus 3.9065M, MTN Academy 2.942M. Total 28.53M against Q1 actual sales of 3.79M. The full-year target is KES 126M. Ask Sales for the pipeline behind Elimu Pepe, which is 48% of the Q2 target.

## Slide 14: Q2 execution: deliverables, owners and measures
3 Q2 PRIORITIES & EXECUTION
Deliverable | Owner | By when | Success measure | What we need
Cash runway report and 12-month forecast | Finance | Mid-month | Runway of 6 months or more shown for the month | Sales forecast each month
Collections: reconcile debtors, escalate accounts, dated recovery milestones | Finance | 31 Oct, then bi-weekly | 95% collections discipline; 50% of invoices paid in 30 days | Sales support on school follow-up
Statutory remittance schedule agreed and executed | Finance | 31 Oct | Statutory accounts reconciled and paid on due dates | Approval of cash release
FY2025/26 audit completed | Finance | 31 Dec | Audit signed off | Timely answers to auditor queries
Recover 5 off-plan actions: Safe Space, manager training, rotation pilot, skills gaps, escalation paths | Operations | 30 Nov to 31 Dec | Owner, date and evidence for each action | Manager time and host departments
Q1 performance reviews using OKR templates; brief staff on bonus rules | Operations | 30 Nov | Every staff member reviewed; bonus rules communicated | KPI assessments from managers
Source: Q1 FY26/27 KPI Status (pending and next steps). Owners, dates and measures are proposals for confirmation.
Notes: What we will deliver, who owns it, by when, how success is measured, and what we need from others. Next steps come from the Q1 KPI Status. Owners, dates and measures are proposals; edit before presenting.

## Slide 15: Q2 : October to December
October
Close and set up
Statutory remittance plan agreed
Start performance reviews
Reconcile debtor balances
Schedule first Safe Space session
November
Execute and review
Mid-quarter sales and cost review
Complete performance reviews
Share survey response with staff
Manager feedback training
Skills-gap assessment
December
Land and plan
Engagement event
Half-year close preparation
Q2 results against targets
Escalation paths documented
Rotation pilot defined
3 Q2 PRIORITIES & EXECUTION
Notes: Dates inside each month are not fixed in the source documents. Add owners and dates once the team agrees.

## Slide 16: What we need from others
Sales: monthly forecast and help following up school debtors
Management: approval of the statutory remittance schedule and audit timeline
Managers: KPI assessments, training time and cross-department hosts
All departments: timely approvals and documents for month-end close
Notes: Close by asking each owner to confirm. Then open for questions.